## Sheet1
ACTIVITY | ASSIGNED MEMBER | DURATION (WEEKS) | WEEK
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Requirement Analysis Phase
Project planning | ALL | 1 | bar: WEEK 2
Determine objective of the study | AFIF | 1 | bar: WEEK 3
Determine scope | ALIF | 1 | bar: WEEK 3
Analyse the existing system of KADA | ALL | 1 | bar: WEEK 3
Analyze system requirement | ALL | 1 | bar: WEEK 3
Create a proposed system | IMAN | 1 | bar: WEEK 3
Comparing the existing system with proposed system | ALIF | 1 | bar: WEEK 3
Determine process model | AFIQ | 1 | bar: WEEK 3
Create process schedule | AFIQ | 1 | bar: WEEK 3
System Requirement Specification (SRS) planning | ALL | 1 | bar: WEEK 3
Software Design Document (SDD) planning | ALL | 1 | bar: WEEK 3
Design Phase
Document system requirement | ALL | 2 | bar: WEEK 4 to WEEK 5
Design use case | IMAN | 1 | bar: WEEK 5
Use Case Description
Use Case 1: Apply for Membership | AFIQ | 1 | bar: WEEK 6
Use Case 2: Apply for Loan | ALIF | 1 | bar: WEEK 6
Use Case 3: Withdraw as Membership | AFIQ | 1 | bar: WEEK 6
Use Case 4: Approve Membership Withdrawal | ALIF | 1 | bar: WEEK 6
Use Case 5: View Financial Statement | IMAN | 1 | bar: WEEK 6
Use Case 6: Update Loan Payment | IMAN | 1 | bar: WEEK 6
Use Case 7: Update Fee Payment | IMAN | 1 | bar: WEEK 6
Use Case 8: Approve Membership Application | AFIQ | 1 | bar: WEEK 6
Use Case 9: Approve Loan Application | ALIF | 1 | bar: WEEK 6
Use Case 10: Manage Loan Policies | ALIF | 1 | bar: WEEK 6
Use Case 11: Generate Report | IMAN | 1 | bar: WEEK 6
Use Case 12: Authentication | IMAN | 1 | bar: WEEK 6
Activity Diagram
Use Case 1: Apply for Membership | AFIQ | 1 | bar: WEEK 6
Use Case 2: Apply for Loan | ALIF | 1 | bar: WEEK 6
Use Case 3: Withdraw as Membership | AFIQ | 1 | bar: WEEK 6
Use Case 4: Approve Membership Withdrawal | ALIF | 1 | bar: WEEK 6
Use Case 5: View Financial Statement | IMAN | 1 | bar: WEEK 6
Use Case 6: Update Loan Payment | IMAN | 1 | bar: WEEK 6
Use Case 7: Update Fee Payment | IMAN | 1 | bar: WEEK 6
Use Case 8: Approve Membership Application | AFIQ | 1 | bar: WEEK 6
Use Case 9: Approve Loan Application | ALIF | 1 | bar: WEEK 6
Use Case 10: Manage Loan Policies | ALIF | 1 | bar: WEEK 6
Use Case 11: Generate Report | IMAN | 1 | bar: WEEK 6
Use Case 12: Authentication | IMAN | 1 | bar: WEEK 6
Sequence Diagram
Use Case 1: Apply for Membership | AFIQ | 1 | bar: WEEK 6
Use Case 2: Apply for Loan | ALIF | 1 | bar: WEEK 6
Use Case 3: Withdraw as Membership | AFIQ | 1 | bar: WEEK 6
Use Case 4: Approve Membership Withdrawal | ALIF | 1 | bar: WEEK 6
Use Case 5: View Financial Statement | IMAN | 1 | bar: WEEK 6
Use Case 6: Update Loan Payment | IMAN | 1 | bar: WEEK 6
Use Case 7: Update Fee Payment | IMAN | 1 | bar: WEEK 6
Use Case 8: Approve Membership Application | AFIQ | 1 | bar: WEEK 6
Use Case 9: Approve Loan Application | ALIF | 1 | bar: WEEK 6
Use Case 10: Manage Loan Policies | ALIF | 1 | bar: WEEK 6
Use Case 11: Generate Report | IMAN | 1 | bar: WEEK 6
Use Case 12: Authentication | IMAN | 1 | bar: WEEK 6
Create UML Class Diagram | IMAN | 1 | bar: WEEK 7
Create SRS Document | ALL | 2 | bar: WEEK 6 to WEEK 7
Create SDD Document | ALL | 2 | bar: WEEK 6 to WEEK 7
Design System Architecture | ALL | 1 | bar: WEEK 7
Design Application Layer | ALL | 1 | bar: WEEK 7
Design Application Layer | ALL | 1 | bar: WEEK 7
Implementation Phase
Coding
Use Case 1: Apply for Membership | AFIQ | 3 | bar: WEEK 9 to WEEK 11
Use Case 2: Apply for Loan | ALIF | 3 | bar: WEEK 9 to WEEK 11
Use Case 3: Withdraw as Membership | AFIQ | 3 | bar: WEEK 9 to WEEK 11
Use Case 4: Approve Membership Withdrawal | ALIF | 3 | bar: WEEK 9 to WEEK 11
Use Case 5: View Financial Statement | IMAN | 3 | bar: WEEK 9 to WEEK 11
Use Case 6: Update Loan Payment | IMAN | 3 | bar: WEEK 9 to WEEK 11
Use Case 7: Update Fee Payment | IMAN | 3 | bar: WEEK 9 to WEEK 11
Use Case 8: Approve Membership Application | AFIQ | 3 | bar: WEEK 9 to WEEK 11
Use Case 9: Approve Loan Application | ALIF | 3 | bar: WEEK 9 to WEEK 11
Use Case 10: Manage Loan Policies | ALIF | 3 | bar: WEEK 9 to WEEK 11
Use Case 11: Generate Report | IMAN | 3 | bar: WEEK 9 to WEEK 11
Use Case 12: Authentication | IMAN | 3 | bar: WEEK 9 to WEEK 11
User Interface Development
Use Case 1: Apply for Membership | AFIQ | 4 | bar: WEEK 9 to WEEK 12
Use Case 2: Apply for Loan | ALIF | 4 | bar: WEEK 9 to WEEK 12
Use Case 3: Withdraw as Membership | AFIQ | 4 | bar: WEEK 9 to WEEK 12
Use Case 4: Approve Membership Withdrawal | ALIF | 4 | bar: WEEK 9 to WEEK 12
Use Case 5: View Financial Statement | IMAN | 4 | bar: WEEK 9 to WEEK 12
Use Case 6: Update Loan Payment | IMAN | 4 | bar: WEEK 9 to WEEK 12
Use Case 7: Update Fee Payment | IMAN | 4 | bar: WEEK 9 to WEEK 12
Use Case 8: Approve Membership Application | AFIQ | 4 | bar: WEEK 9 to WEEK 12
Use Case 9: Approve Loan Application | ALIF | 4 | bar: WEEK 9 to WEEK 12
Use Case 10: Manage Loan Policies | ALIF | 4 | bar: WEEK 9 to WEEK 12
Use Case 11: Generate Report | IMAN | 4 | bar: WEEK 9 to WEEK 12
Use Case 12: Authentication | IMAN | 4 | bar: WEEK 9 to WEEK 12
Document system | ALIF,AFIF | 2 | bar: WEEK 11 to WEEK 12
Software Test Description (STD) planning | ALL | 1 | bar: WEEK 11 to WEEK 12
Create STD Document | ALL | 2 | bar: WEEK 11
Testing Phase
Unit testing
Use Case 1: Apply for Membership | AFIQ | 1 | bar: WEEK 13
Use Case 2: Apply for Loan | ALIF | 1 | bar: WEEK 13
Use Case 3: Withdraw as Membership | AFIQ | 1 | bar: WEEK 13
Use Case 4: Approve Membership Withdrawal | ALIF | 1 | bar: WEEK 13
Use Case 5: View Financial Statement | IMAN | 1 | bar: WEEK 13
Use Case 6: Update Loan Payment | IMAN | 1 | bar: WEEK 13
Use Case 7: Update Fee Payment | IMAN | 1 | bar: WEEK 13
Use Case 8: Approve Membership Application | AFIQ | 1 | bar: WEEK 13
Use Case 9: Approve Loan Application | ALIF | 1 | bar: WEEK 13
Use Case 10: Manage Loan Policies | ALIF | 1 | bar: WEEK 13
Use Case 11: Generate Report | IMAN | 1 | bar: WEEK 13
Use Case 12: Authentication | IMAN | 1 | bar: WEEK 13
Integration Testing
Use Case 1: Apply for Membership | AFIQ | 1 | bar: WEEK 13
Use Case 2: Apply for Loan | ALIF | 1 | bar: WEEK 13
Use Case 3: Withdraw as Membership | AFIQ | 1 | bar: WEEK 13
Use Case 4: Approve Membership Withdrawal | ALIF | 1 | bar: WEEK 13
Use Case 5: View Financial Statement | IMAN | 1 | bar: WEEK 13
Use Case 6: Update Loan Payment | IMAN | 1 | bar: WEEK 13
Use Case 7: Update Fee Payment | IMAN | 1 | bar: WEEK 13
Use Case 8: Approve Membership Application | AFIQ | 1 | bar: WEEK 13
Use Case 9: Approve Loan Application | ALIF | 1 | bar: WEEK 13
Use Case 10: Manage Loan Policies | ALIF | 1 | bar: WEEK 13
Use Case 11: Generate Report | IMAN | 1 | bar: WEEK 13
Use Case 12: Authentication | IMAN | 1 | bar: WEEK 13
System testing | ALL | 1 | bar: WEEK 14
Acceptance testing | ALL | 1 | bar: WEEK 14
Project presentation | ALL | 1 | bar: WEEK 14