## Sheet1
ACTIVITY | ASSIGNED MEMBER | DURATION (WEEKS) | WEEK
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Chapter 1: Introduction
1.1 Introduction | Afiq | 1 | bar: WEEK 2
1.2 Problem Background | Afiq | 1
1.3 Project Aim | Najma | 1
1.4 Project Objectives | Najma | 1
1.5 Project Scope | Brendan | 1
1.6 Project Importance | Brendan | 1
1.7 Report Organization | Afiq | 1
Chapter 2: Literature Review
2.1 Introduction | Mukhritz | 1 | bar: WEEK 4
2.2 Supply Chain Management | Najma | 1 | bar: WEEK 5
2.3 Enterprise Resource Planning | Asyikin | 1 | bar: WEEK 6
2.4 Medallion Architecture | Brendan | 1 | bar: WEEK 6
2.5 Visualisation | Cheryl | 1 | bar: WEEK 6
2.6 Azure / Comparison existing and case study | Pravinraj | 1
2.7 Power BI | Afiq | 1