## Gantt Chart
HR PROJECT GANTT CHART · PPG Industry Data Analytics Project · March – June 2026
[6 empty] | March 2026 |  |  | April 2026 |  |  |  | May 2026 |  |  |  | June 2026
# | Task Name | Task Leader | Start Date | End Date | Duration (Days) | 16 Mar | 23 Mar | 30 Mar | 06 Apr | 13 Apr | 20 Apr | 27 Apr | 04 May | 11 May | 18 May | 25 May | 01 Jun | 08 Jun | 15 Jun
1 | Chapter 1 & 2 | Asyikin & Najma | 17-Mar-2026 | 30-Mar-2026 | 13
2 | Visit to PPG Industry & Gather User Req | All Members | 06-Apr-2026 | 07-Apr-2026 | 1 | bar: April 2026 06 Apr
3 | Chapter 3 | Afiq & Mukhritz | 08-Apr-2026 | 20-Apr-2026 | 12
4 | Chapter 4 | Brendan & Pravinraj | 20-Apr-2026 | 11-May-2026 | 21 | bar: April 2026 20 Apr to May 2026 11 May
5 | Data Architect & Ingestion | Afiq | 20-Apr-2026 | 27-Apr-2026 | 7
6 | Silver Layer: RA Logic | Asyikin | 28-Apr-2026 | 04-May-2026 | 6 | bar: April 2026 27 Apr to May 2026 04 May
7 | Silver Layer: MC Logic | Brendan | 28-Apr-2026 | 04-May-2026 | 6
8 | Silver Layer: Risk & Supply | Cheryl | 28-Apr-2026 | 04-May-2026 | 6 | bar: April 2026 27 Apr to May 2026 04 May
9 | Gold Layer & Data Warehouse | Mukhritz | 05-May-2026 | 11-May-2026 | 6
10 | Chapter 5 & Submission | Cheryl | 11-May-2026 | 15-Jun-2026 | 35 | bar: May 2026 11 May to June 2026 15 Jun
11 | Power BI Developer | Najma | 12-May-2026 | 01-Jun-2026 | 20
12 | Documentation & Quality Lead | Pravinraj | 01-Jun-2026 | 15-Jun-2026 | 14 | bar: June 2026 01 Jun to June 2026 15 Jun

## Legend
TASK LEGEND
# | Task Name | Task Leader | Colour
1 | Chapter 1 & 2 | Asyikin & Najma
2 | Visit to PPG Industry & Gather User Req | All Members
3 | Chapter 3 | Afiq & Mukhritz
4 | Chapter 4 | Brendan & Pravinraj
5 | Data Architect & Ingestion | Afiq
6 | Silver Layer: RA Logic | Asyikin
7 | Silver Layer: MC Logic | Brendan
8 | Silver Layer: Risk & Supply | Cheryl
9 | Gold Layer & Data Warehouse | Mukhritz
10 | Chapter 5 & Submission | Cheryl
11 | Power BI Developer | Najma
12 | Documentation & Quality Lead | Pravinraj